## Sheet1
Connection ID | Operation Number | Attachment Action | Pole Owner | Pole # | SCID | Pole Structure | Proposed Riser | Proposed Guy | PLA (%) with proposed attachment | Construction Grade of Analysis | Existing Mid-Span Data |  | Make Ready Data |  |  |  | One Touch Transfer: Make Ready or Upgrade & Simple or Complex | Remedy Description and Explanation/ Additional Comments/Variance Requests | Responsible Party: Attacher or CPS | Existing CPSE Red Tag on Pole | Pole Data Missing in GIS (if yes fill out Missing Pole Data worksheet) | CPSE Application Comments
[11 empty] | Height Lowest Com | Height Lowest CPS Electrical | Attacher Description | Attachment Height |  | Mid-Span (same span as existing)
[14 empty] | Existing | Proposed | Proposed
-OJ_QO10emfZauaNUM4I | 1 | ( I )nstalling | CPS | PL410620 | 1 | 40-4 | No | No | 82.20 | C | 14'-10" | 25'-8" | CPS ENERGY Neutral | 29'-6" |  |  | None |  | Charter (2) | NO | NO | Install proposed Charter Fiber Optic Com at
[13 empty] | CPS ENERGY Supply Fiber | 28'-0"
[13 empty] | Charter Fiber Optic Com |  | 24'-7" | 21'-1"
[13 empty] | AT&T Fiber Optic Com | 23'-7"
[13 empty] | AT&T Telco Com | 22'-4"
[13 empty] | AT&T Com Drop | 21'-5" |  | 16'-0"
Backspan
[13 empty] | CPS ENERGY Neutral | 29'-6"
[13 empty] | CPS ENERGY Supply Fiber | 28'-0"
[13 empty] | Charter Fiber Optic Com |  | 24'-7"
[13 empty] | AT&T Fiber Optic Com | 23'-7"
[11 empty] | From Pole | To Pole | AT&T Telco Com | 22'-4"
[11 empty] | PL410620 | PL398491 | AT&T Com Drop | 21'-5"
-OP2M3Yf2DfJczUNfA6w | 2 | ( I )nstalling | CPS | PL389359 | 3 | 45-4 | YES (1) | No | 92.00 | C | NA | NA | CPS ENERGY Neutral | 27'-3" |  |  | Make Ready Simple |  | Charter (2) | NO | NO | Install proposed Charter Down Guy at Install proposed Charter Fiber Optic Com at Raise AT&T Fiber Optic Com 8" from 22'-8" to 22'-0" Install proposed Charter Riser at Raise AT&T Telco Com 8" from 21'-8" to 21'-0"
[13 empty] | CPS ENERGY Neutral | 27'-3"
[13 empty] | CPS ENERGY Supply Fiber | 25'-9"
[13 empty] | Charter Down Guy |  | 23'-0"
[13 empty] | Charter Fiber Optic Com |  | 23'-0"
[13 empty] | AT&T Fiber Optic Com | 22'-8" | 22'-0"
[13 empty] | Charter Riser |  | 22'-0"
[13 empty] | AT&T Telco Com | 21'-8" | 21'-0"
REF
[13 empty] | CPS ENERGY Neutral |  |  | 25'-6"
[13 empty] | CPS ENERGY Supply Fiber | 25'-9" |  | 22'-8"
[11 empty] | From Pole | To Pole | AT&T Fiber Optic Com | 22'-8" | 22'-0" | 20'-6"
[11 empty] | PL389359 | UG | AT&T Telco Com | 21'-8" | 21'-0" | 18'-5"
-OJxyAJpFgj-CaetpYWz | 3 | ( I )nstalling | CPS | PL389359 | 3 | 45-4 | YES (1) | No | 92.00 | C | 17'-8" | 22'-8" | CPS ENERGY Neutral | 27'-3" |  |  | Make Ready Simple |  | Charter (2) | NO | NO | Install proposed Charter Down Guy at Install proposed Charter Fiber Optic Com at Raise AT&T Fiber Optic Com 8" from 22'-8" to 22'-0" Install proposed Charter Riser at Raise AT&T Telco Com 8" from 21'-8" to 21'-0"
[13 empty] | CPS ENERGY Neutral | 27'-3"
[13 empty] | CPS ENERGY Supply Fiber | 25'-9"
[13 empty] | Charter Down Guy |  | 23'-0"
[13 empty] | Charter Fiber Optic Com |  | 23'-0" | 18'-8"
[13 empty] | AT&T Fiber Optic Com | 22'-8" | 22'-0" | 17'-2"
[13 empty] | Charter Riser |  | 22'-0"
[13 empty] | AT&T Telco Com | 21'-8" | 21'-0" | 16'-2"
REF
[13 empty] | CPS ENERGY Neutral |  |  | 25'-6"
[13 empty] | CPS ENERGY Supply Fiber | 25'-9" |  | 22'-8"
[11 empty] | From Pole | To Pole | AT&T Fiber Optic Com | 22'-8" | 22'-0" | 20'-6"
[11 empty] | PL389359 | PL404474 | AT&T Telco Com | 21'-8" | 21'-0" | 18'-5"
-OJ_QKap8_9w_POuOX7d | 4 | ( I )nstalling | CPS | PL404474 | 4 | 40-3 | No | No | 62.45 | C | 19'-6" | 25'-6" | CPS ENERGY Neutral | 26'-0" |  |  | Make Ready Simple |  | Charter (2) | NO | NO | Lower AT&T Fiber Optic Com 22" from 22'-9" to 20'-7" Install proposed Charter Fiber Optic Com at Lower AT&T Telco Com 24" from 21'-7" to 19'-7"
[13 empty] | CPS ENERGY Street Light Feed | 26'-0" |  | 24'-6"
[13 empty] | CPS ENERGY Supply Fiber | 24'-6"
[13 empty] | CPS ENERGY Street Light (top of bracket) | 23'-6"
[13 empty] | CPS ENERGY drip_loop (drip_loop) | 23'-0"
[13 empty] | AT&T Fiber Optic Com | 22'-9" | 20'-7" | 19'-1"
[13 empty] | Charter Fiber Optic Com |  | 21'-7" | 20'-7"
[13 empty] | AT&T Telco Com | 21'-7" | 19'-7" | 18'-0"
Backspan
[13 empty] | CPS ENERGY Neutral | 26'-0"
[13 empty] | CPS ENERGY Supply Fiber | 24'-6"
[13 empty] | CPS ENERGY drip_loop (drip_loop) | 23'-0"
[13 empty] | AT&T Fiber Optic Com | 22'-9" | 20'-7"
[11 empty] | From Pole | To Pole | Charter Fiber Optic Com |  | 21'-7"
[11 empty] | PL404474 | PL900997 | AT&T Telco Com | 21'-7" | 19'-7"
-OOZIxBTFE8ctJ5d0c0I | 5 | ( I )nstalling | CPS | PL900997 | 5 | 45-2 | YES (1) | No | 64.17 | C | NA | NA | CPS ENERGY Service | 27'-1" |  |  | Make Ready Simple |  | Charter (2) | NO | NO | Lower AT&T Fiber Optic Com 12" from 21'-6" to 20'-6" Install proposed Charter Fiber Optic Com at Install proposed Charter Down Guy at Install proposed Charter Riser at Lower AT&T Telco Com 12" from 20'-6" to 19'-6"
[13 empty] | CPS ENERGY Street Light Feed | 27'-1"
[13 empty] | CPS ENERGY Neutral | 27'-1"
[13 empty] | CPS ENERGY Supply Fiber | 25'-10"
[13 empty] | CPS ENERGY drip_loop (drip_loop) | 25'-8"
[13 empty] | CPS ENERGY Street Light (top of bracket) | 25'-0"
[13 empty] | CPS ENERGY drip_loop (drip_loop) | 23'-11"
[13 empty] | AT&T Fiber Optic Com | 21'-6" | 20'-6"
[13 empty] | Charter Fiber Optic Com |  | 21'-6"
[13 empty] | Charter Down Guy |  | 21'-6"
[13 empty] | Charter Riser |  | 20'-6"
[13 empty] | AT&T Telco Com | 20'-6" | 19'-6"
REF to PL398490
[13 empty] | CPS ENERGY Neutral | 27'-1" |  | 26'-5"
[13 empty] | CPS ENERGY Street Light Feed | 27'-1" |  | 24'-10"
[13 empty] | CPS ENERGY Supply Fiber | 25'-10" |  | 24'-7"
[13 empty] | AT&T Fiber Optic Com | 21'-6" | 20'-6" | 22'-1"
[13 empty] | AT&T Telco Com | 20'-6" | 19'-6" | 21'-0"
[11 empty] | From Pole | To Pole | REF to PL398490
[11 empty] | PL900997 | UG | CPS ENERGY Service | 27'-1" |  | 12'-0"
-OPCjr3oYEEY70EImQWq | 6 | ( I )nstalling | CPS | PL370858 | 6 | 45-2 | YES (1) | No | 41.95 | C | NA | NA | CPS ENERGY Neutral | 26'-6" |  |  | Make Ready Simple |  | Charter (2) | NO | NO | Lower AT&T Fiber Optic Com 3" from 22'-10" to 21'-1" Install proposed Charter Down Guy at Install proposed Charter Fiber Optic Com at Lower AT&T Telco Com 3" from 21'-10" to 20'-1" Install proposed Charter Riser at
[13 empty] | CPS ENERGY Supply Fiber | 25'-5"
[13 empty] | AT&T Fiber Optic Com | 22'-10" | 21'-1"
[13 empty] | Charter Down Guy |  | 22'-1"
[13 empty] | Charter Fiber Optic Com |  | 22'-1"
[13 empty] | AT&T Telco Com | 21'-10" | 20'-1"
[13 empty] | Charter Riser |  | 21'-1"
REF to PL379971
[13 empty] | CPS ENERGY Neutral | 26'-6" |  | 24'-9"
[13 empty] | CPS ENERGY Supply Fiber | 25'-5" |  | 21'-2"
[13 empty] | AT&T Fiber Optic Com | 22'-10" | 21'-1" | 19'-9"
[13 empty] | AT&T Telco Com | 21'-10" | 20'-1" | 19'-4"
Backspan
[13 empty] | CPS ENERGY Neutral | 26'-6"
[13 empty] | CPS ENERGY Supply Fiber | 25'-5"
[13 empty] | AT&T Fiber Optic Com | 22'-10" | 21'-1"
[11 empty] | From Pole | To Pole | Charter Fiber Optic Com |  | 22'-1"
[11 empty] | PL370858 | UG | AT&T Telco Com | 21'-10" | 20'-1"